# Risk Management Task

| Category | Identified Risks |
| --- | --- |
| Data & Information Risks | 1. Delayed or restricted access to Riot API/replay data. 2. Poor physiological data quality (noisy heart rate/eye tracking). 3. GDPR non-compliance leading to delays in approval. |
| Stakeholder & Communication Risks | 4. Limited availability of coaches or players for scrim participation. 5. Miscommunication about project scope or deliverables. 6. Changing client expectations mid-project (new KPIs, extra features). |
| Methodology & Technical Risks | 7. Synchronization of multimodal data fails to achieve <10 ms accuracy. 8. Dashboard usability lower than expected (coaches find it confusing). 9. Technical stack limitations (server capacity, API rate limits). |
| Timeline & Resource Risks | 10. Scope creep from adding more KPIs/modalities than feasible. 11. Team member absence due to illness or workload. 12. Unexpected delays in setting up sensors or capture environment. |
| External Environment Risks | 13. Riot Games API policy changes that break data access. 14. Tournament schedule conflicts reduce scrim opportunities. 15. Changes in league rules restricting physiological device use. |

| ID | Description | Category | Probability (P) | Impact (I) | Score (P×I) | Priority | Response Strategy |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R001 | Riot API or replay data delayed/unavailable | Data | 2 (Medium) | 3 (High) | 6 | Critical | Mitigation: Cache scrim data locally; use replay parsing tools as backup. |
| R002 | Physiological data too noisy to be usable | Data | 2 (Medium) | 2 (Medium) | 4 | Moderate | Mitigation: Run pilot sessions early, test multiple devices, collect redundant signals. |
| R003 | GDPR approval or consent process delays project start | Data | 1 (Low) | 3 (High) | 3 | Moderate | Avoidance: Draft consent forms and data protection plan by Week 3; pre-approve with BUas ethics team. |
| R004 | Coaches/players unavailable for feedback or scrims | Stakeholder | 3 (High) | 2 (Medium) | 6 | Critical | Mitigation: Schedule sessions well in advance, offer async video demo for feedback. |
| R005 | Misalignment on deliverables (scope misunderstanding) | Stakeholder | 2 (Medium) | 3 (High) | 6 | Critical | Avoidance: Share scoping doc for sign-off early, hold mid-project review to confirm alignment. |
| R006 | Client changes KPI requirements late | Stakeholder | 2 (Medium) | 2 (Medium) | 4 | Moderate | Contingency: Freeze KPI list by Week 4; defer new requests to future phase. |
| R007 | Synchronization fails (<10 ms not met) | Technical | 2 (Medium) | 3 (High) | 6 | Critical | Mitigation: Build early pipeline prototype by Week 5; use relative timestamps if absolute fails. |
| R008 | Dashboard usability too low for adoption | Technical | 2 (Medium) | 3 (High) | 6 | Critical | Mitigation: Run quick coach usability test after v1 release, iterate based on feedback. |
| R009 | API rate limits throttle data collection | Technical | 2 (Medium) | 2 (Medium) | 4 | Moderate | Mitigation: Throttle requests, use local replay data to avoid over-reliance on live API. |
| R010 | Scope creep adds more KPIs/modalities | Timeline | 3 (High) | 3 (High) | 9 | Critical | Avoidance: Strict change control; new requests go to backlog for next sprint. |
| R011 | Team member becomes unavailable | Timeline | 2 (Medium) | 2 (Medium) | 4 | Moderate | Mitigation: Cross-train team members, keep shared documentation. |
| R012 | Sensor setup delays eat into data collection time | Timeline | 2 (Medium) | 2 (Medium) | 4 | Moderate | Contingency: Schedule buffer sessions, prioritize non-physiology data first. |
| R013 | Riot API policy change removes needed endpoints | External | 1 (Low) | 3 (High) | 3 | Moderate | Monitoring: Subscribe to Riot Dev updates, maintain backup replay parsing strategy. |
| R014 | Tournament schedule conflicts with planned testing | External | 2 (Medium) | 2 (Medium) | 4 | Moderate | Mitigation: Plan data collection outside tournament windows, schedule buffer weeks. |
| R015 | League bans physiological sensors | External | 1 (Low) | 3 (High) | 3 | Moderate | Contingency: Focus on telemetry + comms analysis, skip physiology if prohibited. |

Integration Plan

1. Pre–Green Light Risk Actions (Weeks 3 - 4)

- Finalize Scope & KPI List: Lock in a realistic set of KPIs this week to prevent scope creep (R010). Present these to the client during the green light session for approval.

- Pilot Capture & Data Quality Check: Run a quick capture session before the green light presentation to validate data pipeline synchronization (R002, R007). Share early results as proof-of-feasibility.

- Draft GDPR Documentation: Have consent forms, privacy notice, and data handling plan ready to present (R003). Getting early sign-off reduces risk of compliance-related delays.

- Align on Stakeholder Availability: Confirm player scrim schedule and coach feedback sessions for Weeks 5–8 (R004). Present this plan at the green light to secure commitment.

2. Immediate Post–Green Light (Weeks 4 - 5)

- Incorporate Client Feedback: Update scope or KPI definitions only if client explicitly requests changes during the green light session (R005, R006).

- Kick Off Usability Planning: Schedule first coach usability session for dashboard v1 in Week 6 to de-risk adoption (R008).

- Confirm Tournament Dates: Lock down testing sessions to avoid conflicts (R014).

3. Ongoing Monitoring & Reporting (Weeks 5 - 8)

- Weekly Risk Review: Include risk register updates in weekly stand-ups. Focus on critical risks (R001, R004, R007, R008, R010).

- Escalation Triggers: Any risk score ≥6 flagged for mentor review immediately; if blocking, escalate to Bram Heijligers and client contact.

- Update Risk Register: After first coach feedback session, re-evaluate probabilities for adoption/usability risks (R008).

4. Contingency Planning & Buffers

- Technical Fallbacks: If physiology data proves unreliable (R002), switch to telemetry + video-only insights and document this.

- Change Control: New client requests captured but deferred to backlog after Week 4 unless they can be delivered without jeopardizing MVP.

- Time Buffers: Maintain at least 1 week at the end of the block reserved for integration, testing, and presentation polish.

5. Impact on Project Deliverables

- Green Light Presentation: Risk register summary included as a slide to demonstrate readiness.

- Timeline Section in Proposal: Updated to reflect that risk management actions (pilot, scope lock, consent forms) are already in motion.

- Confidence Building: Showing early data capture results + consent workflow will reassure collaborators that technical, ethical, and scheduling risks are under control.